## Sheet1
Milestone | Estimated date of completion | Date of completion | Notes
Research | November 1st | November 1st
Recipe alter and search | November 20th | November 18th
Website server | November 13th | November 15th | Errors with the hosting site delayed the initial launch of the website
UI design | November 20th | Ongoing | While the UI is up to expectations, it can still look better and will be a work in progress